## Tasks
Please put in all the tasks for One month only (Jan tracker means only Jan tasks), User Query, Analysis, Bug Fix, Testing, Documentation, Access Issue. Tasks should be relavent and categorised properly, for job failing if you are giving a build its bug fix not CR such things should be taken care of. Efforts should be put in hours and resanoble time for all tasks.
Application Type | Application | Assigned Month | Assigned Date | Sprint | TFS ID | Task Name | Task Type | Worked by | % Completion | Due Date | End Date | Efforts(Hrs) | Status | Remarks
| URP | November | 2016-11-15 | 1611 | 1008292 | validate sharepoint URL persmission level of Accsys user. | Bug fixing | amrish | 100% | 2016-11-30 | 2016-11-30 | 24 | completed
| URP | November | 2016-11-23 | 1611 | 1008293 | UAT Validation againt .net security compliance update | validation | amrish | 100% | 2016-11-30 | 2016-11-30 | 24 | completed
| URP | November | 2016-11-29 | 1611 | 1008294 | ecotfs to VSTS Migration | Migration | amrish | 5% | 2016-12-15 | 2016-12-15 | 48 | in-progress

## LiveSite Issues
All the Bug fix would be considered as Live site issues, please just don’t write the Mail Subject as Issue description but give a short description of the same. Issue Type can be (version control, documentation,consistency, incorrect solution,User Interface, Performance, logic,design issue, data migration, security,unclear requirements, upgradion issue, others). Issue Cause : 1)Upstream issue:- Caused due to upstream sources, other team . 2)Schema Changes:- Caused due to mapping/schema changes, unnoticed communication. 3)Performance: - Caused due to poor job performance, other team dependency performance. 4)Enviormnetal issue:- Casued due to server issues, connectivity issues, refresh issue, server unaivailability. 5)Engineering issue:- Caused due to code defect, versioning, improper configuration, upgradation issues. 6)Other:-Any other cause(specify in bracket) | [6 empty] | Issue Severity : High , Medium, Low
Application Type | Application | Issue Month | Issue Date | Issue Cause | Issue Type | Issue Description | Root Cause | Action Taken | Severity

## Highlights
All the application highlights, please give crisp and to the point information
Application | Highlights

## LowLights
All the Low lights should be given in this pattern
Application | Description | Root Cause | Action taken

## Other Details
Please give relavant information with timlines, also if you have mentioned any activities planned in last month give the status report of the same this month.
Application | Automation | Migration | Decomissioning

## Key CallOuts
Key Callouts would contain the analysis data of last month and this month. You should be giving application wise callouts as to why this month we have so many issues, CRs, or any other task in particular app. Suppose CAT BI had 4 CR in Dec and in Jan it has 10 CR so why the count has incresed so much. Similarly if some count has gone down that should be explained.
Application | Key Callouts

## Risks
This Page gives a candid forum to express all the risks related to your project, interms of upcoming huge work, bandwidth issues, any major issue with Operations/L2/L3 Team, any long on-going issue and upcoming blockages that you see
Application | Risk | Mitigation Plan | Help Required